## Sheet1
Week | Touchpoint | Channel | Owner | Notes
Wk 1 | CEO + CTO relaunch email | Email | CEO, CTO | Frame as capability shift; encourage, do not mandate
Wk 1 | Engineering all-hands segment | All-hands | CTO | “What changes, what does not” + where to start
Wk 1 | Launch AI Hub v0 | Hub | Program Owner | Quick-start, FAQ, links, known limitations
Wk 1 | Introduce champions | Email + channel post | Program Owner | Names, office hours schedule, how to ask for help
Wk 2 | Getting started training | Live + recording | Champions | Setup, workflows, validation, do’s and don’ts
Wk 2 | Office hours (weekly) | Live | Champions | Collect blockers, create FAQ updates
Wk 2 | Tips burst (2 posts) | Slack or Teams | Champions | 1 quick win + 1 “how to validate” example
Wk 3 | Office hours (weekly) | Live | Champions | Collect blockers, create FAQ updates
Wk 3 | “Win of the week” story | Slack or Teams | Champions | Practical example, not marketing
Wk 3 | Tap Outreach #1 (3 min) | Email | Program Owner | Sentiment, blockers, perceived value
Wk 4 | Office hours (weekly) | Live | Champions | Collect blockers, create FAQ updates
Wk 4 | “Win of the week” story | Slack or Teams | Champions | Practical example, not marketing
Wk 5 | Advanced workflows training | Live + recording | Champions | Refactors, tests, debugging, documentation
Wk 5 | Office hours (weekly) | Live | Champions | Collect blockers, create FAQ updates
Wk 6 | Leadership snapshot | Leadership forum | CTO | DAU + enablement reach + top blockers
Wk 6 | Claude Code pilot kickoff (targeted) | Targeted email | CTO + pilot lead | Clarify differences vs Copilot agent-mode
Wk 6 | Office hours (weekly) | Live | Champions | Collect blockers, create FAQ updates
Wk 6 | Tap Outreach #2 (3 min) | Email | Program Owner | Has usefulness improved? What remains hard?