INTERNAL ALIGNMENT DOCUMENT

EasyVista AI Sales Enablement Assessment

| Document Type: | Internal Scope Alignment (Pre-SOW) |
| --- | --- |
| Client: | EasyVista |
| Engagement Lead: | Henry Yelin (Yelin.io) |
| Delivery Team: | Mike Duncan, Russell |
| Project Start: | December 1, 2025 |
| Current Status: | 50% Complete (as of Jan 21, 2026) |
| Budget (Client): | $10-15K (up to $20K if ROI justified) |

# Purpose of This Document

This document aligns Henry and the delivery team on the current scope, completed work, remaining deliverables, and any scope changes before formalizing a client-facing SOW. It addresses three pain points identified mid-project: scope creep, unclear deliverables, and timeline drift.

# Engagement Overview

## Original Scope (December 2025)

AI Sales Enablement Assessment with three core workstreams:

- Top of Funnel BDR Automation – Increase opportunities from 15-20 to 25-30/quarter per BDR

- RFP Automation Adoption – Get full team using Loopio (change management)

- AI Conversation Coaching – Evaluate Gong/Chorus for multilingual coaching

## Client Objectives

- Build investor narrative showing AI-first ways of working

- Identify 1-2 tools for standardization

- Create business case for budget approval

- Q1 deployment with measurable adoption metrics

# Completed Work

| Date | Activity | Outcome |
| --- | --- | --- |
| Jan 4 | Initial discovery call | Mapped current AI tools, identified standardization opportunity |
| Jan 6 | BDR/Marketing discovery call | Tim insight: wants more leads, not better conversion |
| Jan 8 | Evan call prep | Call guide, tool landscape doc, presentation created |
| Jan 9 | Evan COO call | Budget confirmed ($10-15K), team numbers corrected, Q1 timeline |
| Jan 15 | Alexander call (Evan delegate) | Dripify + Loopio confirmed as Q1 quick wins, Gong deferred |
| Jan 19 | Sales AI call with Patrice, Evan, Alexander | Full project review; Tech DD concerns raised |

# Scope Changes Since Kickoff

The following items have been added to the engagement since the original scope was defined:

| Added Item | Source/Date | Status |
| --- | --- | --- |
| Nooks (BDR calling automation) evaluation slide | Alexander request (Jan 15) | Pending |
| Tech Due Diligence deep-dive | Jan 19 call – exit readiness concerns | IN SCOPE (confirmed) |
| Engineering prioritization follow-up (Ludovic/Loic) | Jan 19 call – April release concerns | OUT OF SCOPE (advisory only) |
| Eurazeo board AI update for Patrice | Jan 19 call – needed EOD Friday | Completed |

# Remaining Deliverables

Based on current understanding, the following deliverables remain:

| Deliverable | Owner | Target Date |
| --- | --- | --- |
| Validate Dripify with BDR team (Tim, Cedric, Christopher) | Mike | Jan 23-24 (calls scheduled) |
| Nooks evaluation slide for ExCom | TBD | TBD |
| Globalize Loopio adoption plan (work with Dalila + Jan) | TBD | TBD |
| Tech DD deep-dive session | TBD | Week of Jan 20 |
| Visual presentation (2-slide deck) for Evan + Alexander | TBD | In progress |
| Final recommendations deck with investor narrative | TBD | End of Q1 |

# Explicitly Out of Scope

- Engineering work or code development

- Ludovic/Loic prioritization – advisory attendance only, no deliverables

- Germany rollout (excluded due to works council complexity)

- Tool implementation or configuration (recommendations only)

- Ongoing managed services or support post-assessment

# Known Risks & Blockers

| Risk | Mitigation |
| --- | --- |
| France adoption resistance – "needs to be France's idea" | Engage Cedric early; position as collaborative |
| Rod bypassing Loopio for ChatGPT | Understand workflow gaps; address in adoption plan |
| No sales methodology identified | Position as follow-on engagement; don't block AI showcase |
| Scope continues to expand without formal change control | This document + subsequent SOW |

# Discussion Points for Henry

- Tech DD scope: Is this truly part of the AI assessment, or should it be a separate mini-engagement?

- Deliverable ownership: Who owns each remaining deliverable (Mike, Russell, Henry)?

- Target end date: When does this engagement conclude? "End of Q1" is vague.

- Client-facing SOW: Should we formalize scope with Evan now, or complete informally?

- Billing alignment: Is current work tracking to the $10-15K budget, or have we exceeded?

# Proposed Next Steps

- Review this document with Henry

- Finalize deliverable ownership and target dates

- Decide whether to present formal SOW to EasyVista

- If yes, create client-facing SOW (Phase 3 of this exercise)

— End of Internal Alignment Document —